## Hoja 1
SPRINT PLANNING TEMPLATE
PROJECT NAME |  | Scrum Master | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Proyecto PANAP |  | Marco F. | 2024-08-19 | 2024-11-30 | 50% | SCOPE STATEMENT
¿Donde se guarda? | Nombre de Tarea | Responsable | Fecha de Inicio | Fecha de Termino | Duracion En Dias | Estado | Prioridad | Comentarios
| SPRINT 0 | Marco F. | 2024-08-19 | 2024-09-15 | 28 | Complete
| Entregables | Marco F. | 2024-10-06 | 2024-10-26 | 21 | Complete
Github/Trello | 1.1_APT122_AutoevaluacionCompetenciasFase1 | Marco F. Bruno A. José c. | 2024-08-19 | 2024-08-24 | 6 | Complete | High
Github/Trello | 1.2_APT122_DiarioReflexionFase1 | Marco F. Bruno A. José c. | 2024-08-19 | 2024-09-07 | 20 | Complete | High
Github/Trello | 1.3_APT122_AutoevaluacionFase1 | Marco F. Bruno A. José c. | 2024-09-07 | 2024-09-07 | 1 | Complete | High
Github/Trello | Presentación idea del Proyecto/ Visión del proyecto | Marco F. José C. | 2024-08-19 | 2024-08-30 | 12 | Complete | High
Github/Trello | 1.4_APT122_FormativaFase1 | Marco F. Carlos C. | 2024-09-07 | 2024-09-07 | 1 | Complete | High
Github/Trello | 1.5_GuiaEstudiante_Fase 1_Definicion Proyecto APT | Marco F. Bruno A. José c. | 2024-08-23 | 2024-09-07 | 16 | Complete | High
Github/Trello | PLANILLA EVALUACION FASE 1 | Marco F. Carlos C. | 2024-09-07 | 2024-09-14 | 8 | Complete | High
| Ámbito Gestion | Marco F. | 2024-08-19 | 2024-09-15 | 28 | Complete
Trello | Sprint Planing | Marco F. | 2024-08-24 | 2024-09-15 | 23 | Complete | High
Trello | Product Backlog | Bruno A. José C. | 2024-08-19 | 2024-08-31 | 13 | Complete | High
Trello | Roadmap | Bruno A. José C. | 2024-09-03 | 2024-09-15 | 13 | Complete | Medium
Trello | Reunión Retrospectiva | Marco F. Bruno A. José C. | 2024-09-10 | 2024-09-15 | 6 | Complete | Medium
Github/Trello | Informe ejecutivo | Marco F. Bruno A. José c. | 2024-09-06 | 2024-09-14 | 9 | Complete | Medium
Trello | Épicas e Historias de usuario. | Bruno A. | 2024-08-31 | 2024-09-03 | 4 | Complete | High
Trello | Burnup Chart | Marco F. Bruno A. José C. | 2024-08-25 | 2024-09-15 | 22 | Complete | Medium
Trello | BurnDown Chart | Marco F. Bruno A. José C. | 2024-08-26 | 2024-09-15 | 21 | Complete | Medium
Trello | Visión del proyecto | Marco F. José C | 2024-08-27 | 2024-08-30 | 4 | Complete | High
Trello | Sprint ¦ Reuniones ¦ Checkpoint | Marco F. José C. Bruno A. | 2024-08-28 | 2024-09-15 | 19 | Complete | High
| Ámbito Diseño | Marco F. | 2024-08-19 | 2024-09-15 | 28 | Complete
Trello | Vistas 4+1 | José C. Bruno A. | 2024-09-03 | 2024-09-12 | 10 | Complete | Low
Trello | Prototipo interactivo | José C. | 2024-08-19 | 2024-08-27 | 9 | Complete | High
Trello | Modelo BBDD | José C. Bruno A. | 2024-09-03 | 2024-09-05 | 3 | Complete | High
Trello | CRUD | José C. | 2024-09-03 | 2024-09-05 | 3 | Complete | Medium
Trello | Diagrama de Flujo | José C. | 2024-09-03 | 2024-09-07 | 5 | Complete | Medium
| Ámbito Desarrollo de software | Marco F. | 2024-08-19 | 2024-09-15 | 28 | Complete
Trello | Tablero kanban (Trello) | Marco F. | 2024-08-19 | 2024-09-14 | 27 | Complete | High
Github | Github | Marco F. Bruno A. José C: | 2024-08-24 | 2024-09-07 | 15 | Complete | High
| SPRINT 1 | Marco F. | 2024-09-15 | 2024-10-05 | 21 | Complete
| Desarrollo | Marco F. | 2024-09-15 | 2024-10-05 | 21 | Complete
Github | Creación de Proyecto Ionic | Bruno A. José C. | 2024-09-16 | 2024-09-21 | 6 | Complete | High
Github | Asignacion de Requerimientos | Bruno A. José C. | 2024-09-16 | 2024-09-21 | 6 | Complete | Medium
Github | Diseño de Interfaz de usuario y tienda | Bruno A. José C. | 2024-09-21 | 2024-10-05 | 15 | Complete | Medium
Github | Diseño de login | Bruno A. José C. | 2024-09-21 | 2024-10-05 | 15 | Complete | Medium
Github | Diseño de menú Principal | Bruno A. José C. | 2024-09-21 | 2024-10-05 | 15 | Complete | Medium
Github | Implementación Servidor Base de datos | Bruno A. José C. | 2024-09-21 | 2024-10-05 | 15 | Complete | High
Github | Desarrollo de Api Rest | Bruno A. José C. | 2024-09-23 | 2024-10-05 | 13 | Complete | High
Github | Integración con API | Bruno A. José C. | 2024-09-28 | 2024-10-05 | 8 | Complete | High
Github | Integración con Base de datos | Bruno A. José C. | 2024-09-28 | 2024-10-05 | 8 | Complete | High
| SPRINT 2 | Marco F. | 2024-10-06 | 2024-10-26 | 21 | In Progress
| Desarrollo | Marco F. | 2024-10-06 | 2024-10-26 | 21 | In Progress
Github | Pruebas de Integración con API | Bruno A. José C. | 2024-10-06 | 2024-10-09 | 4 | Complete | High
Github | Diseño de Registro | Bruno A. José C. | 2024-10-06 | 2024-10-14 | 9 | Complete | High
Github | Implementación de funcionalidades ambito de usuario | Bruno A. José C. | 2024-10-10 | 2024-10-26 | 17 | Complete | High
Github | Implementación de funcionalidades ámbito de Tienda | Bruno A. José C. | 2024-10-10 | 2024-10-26 | 17 | In Progress | High
Github | Implementación API de google maps | Marco F. Bruno A. José C. | 2024-10-10 | 2024-10-26 | 17 | Complete | High
| Entregables | Marco F. |  |  | 21
Github/Trello | 2.4_GuiaEstudiante_Fase 2_DesarrolloProyecto APT | Marco F. José C. Bruno A. | 2024-10-06 | 2024-10-26 | 21 | Complete | High
Github/Trello | Planilla de Evaluación de Avance Fase 2 | Marco F. Carlos C. | 2024-10-27 | 2024-10-26 | 21 | In Progress | High
Github/Trello | Presentación del proyecto | Marco F. José C. Bruno A. | 2024-10-27 | 2024-10-26 | 21 | Complete | High
Github/Trello | Evidencias de Documentación | Marco F. José C. Bruno A. | 2024-10-27 | 2024-10-26 | 21 | Complete | High
Github/Trello | Evidencias de Sistemas, Aplicación, Bases de Datos | Marco F. José C. Bruno A. | 2024-10-27 | 2024-10-26 | 21 | Complete | High
| SPRINT 3 | Marco F. | 2024-10-27 | 2024-11-16 | 21 | Not Started
Github | Revisión de Errores | Bruno A. José C. | 2024-10-27 | 2024-11-02 | 7 | Not Started | Medium
Github | Validación de Funcionalidades | Bruno A. José C. | 2024-10-27 | 2024-11-02 | 7 | Not Started | High
Trello | Tablero kanban (Trello) | Marco F. | 2024-10-27 | 2024-11-16 | 21 | In Progress | High
Github | Github | Marco F. Bruno A. José C: | 2024-10-27 | 2024-11-16 | 21 | In Progress | High
| Entregables | Marco F. | 2024-10-27 | 2024-11-16 | 21 | In Progress | High
Github/Trello | Apellido_Nombre_2.1_APT122_DiarioReflexionFase2 | Marco F. José C. Bruno A. | 2024-10-27 | 2024-11-16 | 21 | Complete | High
Github/Trello | Planilla de Evaluación de Avance Fase 2 | Marco F. Carlos C. | 2024-10-27 | 2024-11-16 | 21 | Not Started | High
Github/Trello | 2.6_GuiaEstudiante_Fase 2_Informe Final Proyecto APT | Marco F. José C. Bruno A. | 2024-10-27 | 2024-11-16 | 21 | Not Started | High
Github/Trello | Planilla de Evaluación Final Fase 2 | Marco F. Carlos C. | 2024-10-27 | 2024-11-16 | 21 | In Progress | Low
| SPRINT 4 | Marco F. | 2024-11-17 | 2024-11-30 | 14 | Not Started
| Entregables | Marco F. | 2024-11-17 | 2024-11-30 | 14 | Not Started
Github/Trello | Apellido_Nombre_3.1_APT122_DiarioReflexionFase3 | Marco F. José C. Bruno A. | 2024-11-17 | 2024-11-30 | 14 | Not Started | High
Github/Trello | Planilla de Evaluación Fase 3 | Marco F. Carlos C. | 2024-11-17 | 2024-11-30 | 14 | Not Started | High
Github/Trello | Presentación Final del Proyecto | Marco F. José C. Bruno A. | 2024-11-17 | 2024-11-30 | 14 | Not Started | High
Trello | Tablero kanban (Trello) | Marco F. | 2024-11-17 | 2024-11-30 | 14 | In Progress | High
Github | Github | Marco F. Bruno A. José C: | 2024-11-17 | 2024-11-30 | 14 | In Progress | High

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
Trello / Github | PRIORITY | STATUS
Trello | Low | Not Started
Github | Medium | In Progress
Github/Trello | High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.